## Sheet1
Potential Risk | Risk Level | Mitigation Strategy
Team members unfamiliar with React.js / PostgreSQL | Medium | Schedule early learning sessions, use online tutorials, and simplify functionality if needed.
Limited time due to short project duration and coursework workload | High | Create a weekly plan, prioritize MVP (core features), and conduct weekly progress checks.
Team member absence (illness, scheduling conflicts) | Medium | Assign backup responsibilities, ensure at least two members understand each module, and share code via GitHub.
Requirement changes (feedback from instructor) | Medium | Adopt iterative development (Sprints), reserve buffer time, and use modular design to reduce change cost.
Data loss or version conflicts in team collaboration | Medium | Use Git/GitHub for version control, follow a branching strategy, and back up the database regularly.
UI/UX complexity delays progress | Low | Focus on functional correctness first, polish the UI at later stages.
Insufficient testing leads to defects | Medium | Perform unit and manual tests after each feature completion to validate incrementally.
Deployment or environment compatibility issues | Low | Standardize development environment (Node.js version, DB setup) early and provide README deployment guide.